## Sheet1
Change Request ID | Date Submitted | Submitted By | Description of Change | Reason / Justification | Impact Analysis | Priority | Approval Status | Approved By & Date
1 | 2025-06-12 | Exam Controller | online exam registeration module for students | reduce paperwork, reduce queues,donot visit university as a inperson for registeration | Core module, need database, login/signup UI, EXAM REGISTERATION form UI. | HIGH | aproved | 2026-06-13
2 | 2026-06-11 | Project Manager | Need Admin dashboard, generate report for students grade download/export excel format. | Admin/exam controller needs reports without IT help. | Admin Dashbord, export.download Business logic. | Medium | approved | Project Manager 13-June-2026
3 | 2026-06-13 | Tech Lead | Implement password reset via OTP/Email. | Enhance security and allow self-service for students locked out. | Integrate Email/SMS gateway, update login UI and backend auth. | HIGH | Pending
4 | 2026-06-14 | QA Lead | Add dark mode toggle in student dashboard | Improve user accessibility and experience for night users. | Frontend CSS changes only, no database impact. | Low | approved | Project Manager 15-June-2026